## Summary
IntelliQE — MVP1 & MVP2 Delivery Tracker
Features crawled from MVP1-Planner.xlsx & MVP2-Planner.xlsx, mapped to the IntelliQE codebase. Status set by code inspection (planner status columns were blank). Generated 2026-10-19.
AT A GLANCE
Scope | Total | Done | Partial | Pending | % Done
MVP1 (core platform, IQE-001..037) | 37 | 35 | 2 | 0 | 95%
MVP2 (depth & governance) | 40 | 13 | 19 | 8 | 32%
COMBINED | 77 | 48 | 21 | 8 | 62%
STATUS KEY
Done | Shipped & verified in code
Partial | Exists but needs hardening/finish
Pending | Not started — net-new build
HEADLINE
• MVP1 is effectively complete: every input, agent, execution, integration and deployment feature is live in code.
• The only MVP1 item needing work is SSO/RBAC — SSO is live, but role permissions are advisory (not enforced on routes).
• Most MVP2 'depth' (API full-suite, mock server, contract, TestRail/Zephyr/qTest sync, GitLab/Bitbucket/Azure CI) already shipped as part of API Studio.
• The real MVP2 gaps cluster in 4 themes: enterprise security/governance, observability & cost, core-web rendering surfaces, and analytics persistence.
• 9 items are true net-new builds (Pending); 20 are Partial (finish/harden). See the 'Pending & Priority' tab for the ordered plan.

## MVP1 Status
MVP1 — Core Platform Status
IQE-001..037. 35 Done · 2 Partial · 0 Pending.
ID | Layer | Feature | Status | What exists / What's left | Priority
IQE-001 | Inputs | Jira Integration (API) | Done | jira.service.ts + jira.routes.ts — stories import + bug push live. | P1
IQE-002 | Inputs | Azure DevOps Integration (API) | Done | azure-devops.service.ts + routes — work-item import + bug push. | P1
IQE-003 | Inputs | Confluence | Done | confluence.service.ts + confluence.routes.ts — page import. | P1
IQE-004 | Inputs | SharePoint | Done | sharepoint.service.ts + sharepoint.routes.ts — document import. | P1
IQE-005 | Inputs | Paste Requirements (Prompt) | Done | ChatPage wizard accepts free-text requirement prompt. | P1
IQE-006 | Inputs | Document Upload (PDF/Word/BRD/FRD) | Done | Upload parsed into requirement agent pipeline. | P1
IQE-007 | Inputs | Explore App - Live Application Crawl | Done | exploreAgent.ts crawls live app, derives flows. | P1
IQE-008 | Agents | Requirement Agent | Done | requirementAgent.ts — parses intent + edge cases. | P1
IQE-009 | Agents | Planner Agent | Done | plannerAgent.ts — test strategy + plan. | P1
IQE-010 | Agents | Generator Agent | Done | generatorAgent.ts + scriptAgent.ts — Playwright JS/TS. | P1
IQE-011 | Agents | Healer Agent | Done | healingAgent.ts — flaky/UI-change heal + re-run. | P1
IQE-012 | Execution | Playwright Automation Framework (JS/TS) | Done | playwright-runner.service.ts — e2e execution. | P1
IQE-013 | Execution | Multi-Browser (Chromium/Firefox/WebKit) | Done | Env-driven WEB_TEST_BROWSERS; Chromium default, FF/WebKit opt-in. | P1
IQE-014 | Execution | Mobile Viewport Emulation | Done | web-responsive.service.ts device/viewport emulation. | P1
IQE-015 | Execution | Test Execution Report (Allure & HTML) | Done | HTML reports live; Allure-style breakdown in ReportsPage. | P1
IQE-016 | Execution | GitHub Code Push | Done | git/github.provider.ts — branch commit + PR. | P1
IQE-017 | App Support | Standard HTML DOM Web Apps | Done | Core target — server-rendered + SPA. | P1
IQE-018 | App Support | Single Page Apps (React/Vue/Angular) | Done | Route/state transitions handled by Playwright. | P1
IQE-019 | App Support | Mobile Web - Responsive (Emulated) | Done | Viewport breakpoints via web-responsive. | P1
IQE-020 | Integrations | TestRail CSV Export | Done | api-tm-connectors.service.ts (export path). | P1
IQE-021 | Integrations | GitHub Actions (CI/CD) | Done | cli/ci/ action.yml + api-cicd-connectors. | P1
IQE-022 | Integrations | Jenkins (CI/CD) | Done | cli/ci/Jenkinsfile.example + cicd-connectors. | P1
IQE-023 | Integrations | Jira Bug Push (Bug Tracker) | Done | bugs.routes.ts -> jira.service auto-create on failure. | P1
IQE-024 | Integrations | ADO Bug Push (Bug Tracker) | Done | bugs.routes.ts -> azure-devops.service. | P1
IQE-025 | Integrations | Email Notifications | Done | email.service.ts SMTP on completion/failure. | P1
IQE-026 | Integrations | Slack Notifications | Done | notification-dispatcher + webhook-notification services. | P2
IQE-027 | Integrations | Microsoft Teams Notifications | Done | notification-dispatcher + webhook-notification services. | P2
IQE-028 | Security | SSO / RBAC | Partial | SSO (OIDC/SAML) live via api-sso-public + api-access. RBAC is ADVISORY only — requirePermission applied to NO route; enforce it. | P2
IQE-029 | Security | In-Tenant Sidecar Deployment | Done | Dockerised sidecar, customer-provisioned infra. | P1
IQE-030 | Security | Kill Switch A - Container Stop | Partial | Relies on customer orchestrator stop (inherent to Docker). No in-app verified <30s teardown signal. | P1
IQE-031 | Security | Kill Switch B - TTL License Expiry | Done | license-expiry.middleware.ts startup+runtime gate. | P1
IQE-032 | Security | In-Tenant Data Containment | Done | Customer API keys at runtime; JBS stores none. | P1
IQE-033 | AI/LLM | Claude (Anthropic) - Primary LLM | Done | claude-runner.ts routes all agent reasoning. | P1
IQE-034 | AI/LLM | Customer-Provided API Keys | Done | getTenantLlm reads per-tenant key at runtime. | P1
IQE-035 | Analytics | Self-Healing Outcome Log | Done | Heal attempts + outcomes logged, shown in report. | P1
IQE-036 | Deployment | Standard VNet Sidecar - Azure | Done | Container in customer Azure VNet. | P1
IQE-037 | Deployment | Docker Container | Done | Dockerfile — deploys into customer orchestration. | P1

## MVP2 Status
MVP2 — Depth, Integrations & Governance Status
MVP2 rows from MVP2-Planner Sheet2. Many shipped early via API Studio; gaps are security, observability & core-web rendering.
ID | Layer | Feature | Status | What exists / What's left | Priority
IQE-017 | App Support | REST API (Basic via Crawl) | Done | API Studio captures + validates API calls from flows. | P1
-- | Execution | GitLab Code Push | Done | git/gitlab.provider.ts — commit + MR. | P2
-- | Execution | BitBucket Code Push | Done | git/bitbucket.provider.ts — commit + PR. | P2
IQE-005 | Inputs | Screenshot & Code Snippet Ingestion | Partial | api-multimodal.service (screenshots->brief) done on API side; web-side snippet ingestion not wired. | P1
IQE-035 | Execution | CI/CD Event Triggers | Partial | API CI run token live; PR/commit webhook is capture-only, no auto-run for the core web pipeline. | P2
IQE-036 | Agents | Audit Agent | Partial | auditAgent + traceability log user/API actions; per-agent DECISION trail not fully structured. | P2
IQE-037 | Execution | Parallel Execution (Workers) | Done | api-exec-queue.service.ts configurable slots; API_TEST_WORKERS. | P2
IQE-038 | Execution | Load & Performance Profiling | Done | api-loadtest + loadprofile + web-perf services. | P2
IQE-039 | Execution | Pipeline Templates (Smoke/Regression/Full) | Partial | Scheduler/CI/env done; no named Smoke/Regression/Full suite templates. | P2
IQE-040 | Execution | Steerable Execution (Pause/Skip/Retry) | Pending | No pause/skip/retry mid-run control exists. Net-new build. | P2
IQE-041 | App Support | Shadow DOM / Web Components | Pending | No shadowRoot handling in web agents. Net-new (Salesforce/Fluent). | P2
IQE-042 | App Support | iFrame-embedded Content | Pending | No frameLocator handling. Net-new (cross-origin iframes). | P2
IQE-043 | App Support | Hybrid DOM + Canvas (DOM layer) | Pending | No canvas/DOM-shell handling. Net-new. | P2
IQE-044 | App Support | REST API Full Suite (OpenAPI/Swagger) | Done | api-import parseOpenapi -> full generated suite + auth. | P2
IQE-045 | App Support | GraphQL Testing | Partial | SDL/introspection import generates ops; errors[] contract NOT validated (generic HTTP assert). | P2
IQE-046 | App Support | Contract & Schema Validation | Done | Contract validation + api-drift structural diff. | P2
IQE-047 | App Support | Mock Server (WireMock/Prism) | Done | api-mock.service.ts hosted mock (public /mock route). | P2
IQE-048 | Integrations | TestRail Direct API Sync | Done | api-tm-connectors — create run + post results via API. | P2
IQE-049 | Integrations | GitLab CI Integration | Done | api-cicd-connectors + cli/ci/gitlab-ci.example.yml. | P2
IQE-050 | Integrations | Azure DevOps Pipelines | Done | api-cicd-connectors Azure Pipelines connector. | P2
IQE-051 | Integrations | GitLab Code Push | Done | git/gitlab.provider.ts. | P2
IQE-052 | Integrations | ADO Repos Code Push | Pending | parseRepoUrl supports github/gitlab/bitbucket only; no dev.azure.com provider. | P2
IQE-056 | Security | MFA & Session Management | Partial | TOTP MFA enforced only for enrolled users; session timeout global-only. | P2
IQE-057 | Security | Secret Vault Integration (Key Vault/Vault) | Partial | api-oauth resolveSecret exists but opt-in; creds still stored encrypted in DB. | P2
IQE-058 | Security | Compliance Audit Log Viewer | Partial | Viewer + CSV export done; no PDF export. | P2
IQE-059 | Security | Data Retention & Auto-Purge | Partial | Hardcoded newest-N prune; no per-tenant policy / expiry. | P2
IQE-060 | Security | IP Allowlist / Blocklist | Pending | No network-level allowlist middleware. Net-new. | P2
IQE-061 | Security | Per-Tenant AI Budget Enforcement | Partial | FinOps is a pre-run estimator; no live token tracking / throttle. | P2
IQE-062 | Security | Row-Level Database Security | Pending | Tenancy is app-layer WHERE tenant_id; no DB-enforced RLS. Net-new. | P2
IQE-063 | AI/LLM | Reasoning Effort Controls (per stage) | Partial | Global effort works; per-stage StageDefinition.effort plumbed but never sent to LLM (dead field). | P2
IQE-064 | AI/LLM | Cost Attribution & Token Monitoring | Partial | Per-run USD stored; no tokens-per-agent attribution / dashboard / export. | P2
IQE-065 | AI/LLM | Agent Performance Scoring | Partial | In-memory last-200 metrics; no trend / accuracy / false-positive / cost. | P2
IQE-066 | AI/LLM | Self-Healing Performance Metrics | Partial | Per-run heal counts; no aggregate heal-rate / accuracy. | P2
IQE-067 | Analytics | Coverage Trend Dashboards (Sprint/Release) | Partial | TestRail + run-over-run pass-rate; no sprint/release coverage trend. | P2
IQE-068 | Analytics | Flakiness Intelligence & Auto-Quarantine | Partial | Flaky detect + MANUAL quarantine; no auto-quarantine / trend. | P2
IQE-069 | Analytics | AI Agent Analytics (tokens/accuracy/cost) | Partial | Per-agent dashboard shows duration+success only; no tokens/cost. | P2
IQE-070 | Analytics | Scheduled Report Delivery | Partial | Trigger emails only; no daily/weekly digest schedule. | P2
IQE-071 | Analytics | Unified Web & API Reporting Dashboard | Done | reports.routes /history merges web+api; ReportsPage renders combined. | P2
IQE-073 | Deployment | VNet Complexity - Custom Config (Ad Hoc) | Pending | No documented assessment/scoping process. Net-new (process). | P2
IQE-074 | Deployment | Automated Tenant Onboarding | Partial | Signup auto-creates tenant; no guided setup wizard. | P2

## Pending & Priority
Pending & Partial — Prioritized Build Plan
Everything not fully Done across MVP1 + MVP2, ranked. Rank 1 = do first. Grouped by theme; enterprise blockers lead.
Rank | ID | MVP | Feature | Status | What's left to do | Priority | Theme
1 | IQE-028 | MVP1 | SSO / RBAC enforcement | Partial | Apply requirePermission/requireRole to protected routes — currently advisory only. | P1 | Enterprise blocker
2 | IQE-062 | MVP2 | Row-Level Database Security | Pending | Enforce tenancy at DB layer (RLS / security policy), not just app-layer WHERE. | P2 | Enterprise blocker
3 | IQE-060 | MVP2 | IP Allowlist / Blocklist | Pending | Add network-level allow/block middleware, configurable per tenant. | P2 | Enterprise blocker
4 | IQE-057 | MVP2 | Secret Vault Integration | Partial | Make vault the default credential source; stop storing creds in DB. | P2 | Enterprise blocker
5 | IQE-059 | MVP2 | Data Retention & Auto-Purge | Partial | Per-tenant retention policy + scheduled expiry purge (90-day std). | P2 | Enterprise blocker
6 | IQE-056 | MVP2 | MFA & Session Management | Partial | Enforce MFA tenant-wide; per-tenant configurable session timeout. | P2 | Enterprise blocker
7 | IQE-030 | MVP1 | Kill Switch A - Container Stop | Partial | Verified <30s teardown signal / health-gate inside the app. | P1 | Security
8 | IQE-064 | MVP2 | Cost Attribution & Token Monitoring | Partial | Persist tokens + USD per run/agent/tenant; dashboard + export. | P2 | Observability & cost
9 | IQE-061 | MVP2 | Per-Tenant AI Budget Enforcement | Partial | Live token tracking + throttle on budget breach. | P2 | Observability & cost
10 | IQE-063 | MVP2 | Reasoning Effort Controls (per stage) | Partial | Send StageDefinition.effort to the LLM (wire the dead field). | P2 | Observability & cost
11 | IQE-066 | MVP2 | Self-Healing Performance Metrics | Partial | Aggregate heal-rate / accuracy / failure-reason metrics. | P2 | Observability & cost
12 | IQE-065 | MVP2 | Agent Performance Scoring | Partial | Persist scores; add trend, accuracy, false-positive, cost. | P2 | Observability & cost
13 | IQE-069 | MVP2 | AI Agent Analytics (tokens/accuracy/cost) | Partial | Add tokens + cost to the per-agent analytics dashboard. | P2 | Observability & cost
14 | IQE-068 | MVP2 | Flakiness Intelligence & Auto-Quarantine | Partial | Auto-quarantine flaky tests + flakiness trend over time. | P2 | Analytics
15 | IQE-067 | MVP2 | Coverage Trend Dashboards | Partial | Sprint/release coverage trend view (beyond pass-rate). | P2 | Analytics
16 | IQE-070 | MVP2 | Scheduled Report Delivery | Partial | Daily/weekly digest scheduling (beyond trigger emails). | P2 | Analytics
17 | IQE-058 | MVP2 | Compliance Audit Log Viewer | Partial | Add PDF export alongside the existing CSV. | P2 | Analytics
18 | IQE-036 | MVP2 | Audit Agent | Partial | Structured per-agent decision trail (not just user/API actions). | P2 | Analytics
19 | IQE-041 | MVP2 | Shadow DOM / Web Components | Pending | shadowRoot traversal in web agents (Salesforce Lightning/Fluent). | P2 | Core-web rendering
20 | IQE-042 | MVP2 | iFrame-embedded Content | Pending | frameLocator handling for cross-origin iframes. | P2 | Core-web rendering
21 | IQE-043 | MVP2 | Hybrid DOM + Canvas (DOM layer) | Pending | Test DOM shell of canvas apps; scope canvas out to MVP3. | P2 | Core-web rendering
22 | IQE-040 | MVP2 | Steerable Execution (Pause/Skip/Retry) | Pending | Operator pause/skip/retry of steps mid-run. | P2 | Core-web execution
23 | IQE-045 | MVP2 | GraphQL Testing | Partial | Validate errors[] contract (HTTP 200 + errors should fail). | P2 | API depth
24 | IQE-005 | MVP2 | Screenshot & Code Snippet Ingestion | Partial | Wire snippet/screenshot ingestion into the WEB pipeline. | P1 | Inputs
25 | IQE-035 | MVP2 | CI/CD Event Triggers | Partial | Auto-run core web pipeline on PR/commit webhook (not capture-only). | P2 | CI/CD
26 | IQE-052 | MVP2 | ADO Repos Code Push | Pending | Add dev.azure.com git provider + parseRepoUrl support. | P2 | CI/CD
27 | IQE-039 | MVP2 | Pipeline Templates (Smoke/Regression/Full) | Partial | Three named reusable suite templates. | P2 | Execution
28 | IQE-074 | MVP2 | Automated Tenant Onboarding | Partial | Guided self-service setup wizard. | P2 | Deployment
29 | IQE-073 | MVP2 | VNet Custom Config (Ad Hoc) | Pending | Documented assessment + scoping/pricing process. | P2 | Deployment / process