## Assumptions
ADA Compliance Suite - Roadmap Assumptions
Every date in this workbook is driven by the four blue input cells below. Change them and the whole plan recalculates.
INPUTS - edit these
Project start date | 2026-09-14 | First working day. Must be a Monday-Friday.
Engineers on the feature | 2 | Full-stack engineers assigned.
Allocation per engineer | 80% | Share of time on this feature (0.8 = 80%).
Effective capacity (person-days per working day) | 1.6 | Engineers x allocation. Converts effort into elapsed days.
DERIVED - do not edit
Total effort (person-days) | 171 | Sum of every task on the Roadmap tab.
Elapsed working days | 107 | Total effort divided by effective capacity.
Elapsed calendar weeks | 21.4 | Working days / 5. Excludes public holidays.
MVP delivery (Milestone M3) | 2026-11-11 | Accessibility + broken links + best practices.
Full GA delivery (Milestone M7) | 2027-03-10 | All nine checks, reporting and UI.
BASIS OF ESTIMATE - read before quoting these dates
- Effort figures are engineering estimates produced from a read of this codebase (backend/src/agents, backend/src/orchestrator, backend/src/services, frontend/src/pages/ChatPage.tsx). They are not quotes from the delivery team and have not been validated against team velocity.
- The schedule models tasks as one sequential critical path at the stated capacity. Real execution will parallelise some tracks (e.g. frontend alongside backend checks), which pulls dates in; unplanned work and context-switching push them out. Treat the dates as a planning baseline, not a commitment.
- Public holidays and leave are NOT modelled. WORKDAY() excludes weekends only. Subtract your own holiday days from the delivery dates.
- Phase 3 (Visual & Design QA) carries the widest estimate range. Alignment, overlap and style-guide adherence have no off-the-shelf engine - unlike accessibility, which axe-core solves. If the Phase 0 spike shows a baseline-diff approach is needed, Phase 3 effort could grow materially.
- Recommendation: ship Milestone M3 as release 1. Accessibility and broken links are the highest-confidence, highest-value checks and reach users in roughly a third of the total timeline.

## Roadmap
ADA Compliance Suite - Implementation Roadmap
Dates are formulas driven by the Assumptions tab. Effort is in person-days; Duration converts that to elapsed working days at the assumed team capacity. Weekends excluded, public holidays are not.
ID | Phase | Task | Deliverable / definition of done | Owner | Effort (person-days) | Duration (working days) | Start | End | Milestone | Confidence | Key files / components | Scope tag
1 | Phase 0 - Discovery & Spike | Spike: axe-core on a real target | Run @axe-core/playwright against a live client site. Measure rule coverage, false-positive rate and runtime per page. | Backend eng | 3 | 2 | 2026-09-14 | 2026-09-15 |  | High | backend/src/agents/exploreAgent.ts | A11Y
2 | Phase 0 - Discovery & Spike | Spike: visual-check feasibility | Decide geometry analysis (bounding boxes from the live DOM) vs rendered-baseline diff for alignment/overlap. Prototype both on one page. | Backend eng | 4 | 3 | 2026-09-16 | 2026-09-18 |  | Low | new: backend/src/services/ada-visual.service.ts | ALIGN
3 | Phase 0 - Discovery & Spike | Scope lock & acceptance criteria | Fix WCAG level (2.2 AA), viewport matrix, page-count cap per scan, per-tenant cost budget, and what counts as a pass. | Product + QA lead | 2 | 2 | 2026-09-21 | 2026-09-22 |  | High | backend/config/pipeline-definition.json | INFRA
4 | Phase 0 - Discovery & Spike | Technical design & schema draft | Design doc covering scan lifecycle, finding model, severity taxonomy and DB schema. Reviewed and signed off. | Tech lead | 3 | 2 | 2026-09-23 | 2026-09-24 | M1 - Approach approved | High | backend/src/db.ts | INFRA
5 | Phase 1 - Scan Infrastructure | Extract reusable crawler | Promote the bounded crawl in exploreAgent.ts into ada-crawler.service.ts: auth-aware, same-origin, depth/page caps, emits a sitemap. | Backend eng | 6 | 4 | 2026-09-25 | 2026-09-30 |  | High | backend/src/agents/exploreAgent.ts -> services/ada-crawler.service.ts | INFRA
6 | Phase 1 - Scan Infrastructure | Database schema | ada_scans, ada_findings, ada_baselines tables with tenant_id on every row. Idempotent init, consistent with existing db.ts pattern. | Backend eng | 4 | 3 | 2026-10-01 | 2026-10-05 |  | High | backend/src/db.ts | INFRA
7 | Phase 1 - Scan Infrastructure | Scan orchestration service | ada-scan.service.ts: per-page fan-out, partial-failure tolerance, resumable runs, cost accounting. | Backend eng | 6 | 4 | 2026-10-06 | 2026-10-09 |  | Medium | new: backend/src/services/ada-scan.service.ts | INFRA
8 | Phase 1 - Scan Infrastructure | Worker task type | New task type in the polling worker so scans run out-of-process like pipeline stages do. | Backend eng | 4 | 3 | 2026-10-12 | 2026-10-14 |  | High | backend/src/worker/, routes/pipeline-worker.routes.ts | INFRA
9 | Phase 1 - Scan Infrastructure | SSE progress events | Emit per-page scan progress to the frontend over the existing SSE channel. | Backend eng | 2 | 2 | 2026-10-15 | 2026-10-16 |  | High | backend/src/services/sse-manager.ts | INFRA
10 | Phase 1 - Scan Infrastructure | REST API | ada.routes.ts: start scan, poll status, list findings, fetch one finding. Tenant-scoped, mounted in index.ts. | Backend eng | 4 | 3 | 2026-10-19 | 2026-10-21 | M2 - Scan pipeline runs end-to-end | High | new: backend/src/routes/ada.routes.ts | INFRA
11 | Phase 2 - Deterministic Checks | Accessibility engine (ADA / WCAG) | @axe-core/playwright per page. Map each violation to its WCAG 2.2 success criterion. Alt text, ARIA, focus order, keyboard traps, contrast. | Backend eng | 6 | 4 | 2026-10-22 | 2026-10-27 |  | High | new: backend/src/services/ada-a11y.service.ts | A11Y
12 | Phase 2 - Deterministic Checks | Broken & dead link checker | Crawl every internal and outbound link. Report 404s, redirect chains, timeouts and unreachable targets with the referring page. | Backend eng | 5 | 4 | 2026-10-28 | 2026-11-02 |  | High | new: backend/src/services/ada-links.service.ts | LINKS
13 | Phase 2 - Deterministic Checks | Web best-practice checks | Semantic HTML, page metadata, image sizing, console errors, mixed content. Lighthouse-style rule set. | Backend eng | 5 | 4 | 2026-11-03 | 2026-11-06 |  | Medium | new: backend/src/services/ada-bestpractice.service.ts | BESTPRACTICE
14 | Phase 2 - Deterministic Checks | Finding normalisation | Common finding shape, severity model, cross-page dedupe, element attribution (selector + screenshot region). | Backend eng | 4 | 3 | 2026-11-09 | 2026-11-11 | M3 - MVP: a11y + links shippable | Medium | new: backend/src/services/ada-findings.service.ts | REPORT
15 | Phase 3 - Visual & Design QA | Computed-style harvester | Capture per-element computed styles and bounding boxes at each viewport in the matrix. Shared input for the four visual checks. | Backend eng | 5 | 4 | 2026-11-12 | 2026-11-17 |  | Medium | new: backend/src/services/ada-visual.service.ts | ALIGN
16 | Phase 3 - Visual & Design QA | Font consistency check | Cluster font family/weight/size across pages, flag outliers against the dominant set or the declared type scale. | Backend eng | 5 | 4 | 2026-11-18 | 2026-11-23 |  | Medium | ada-visual.service.ts | FONT
17 | Phase 3 - Visual & Design QA | Colour accuracy check | Compare rendered hex values against the approved palette / design tokens. Flag near-miss and off-palette colours. | Backend eng | 5 | 4 | 2026-11-24 | 2026-11-27 |  | Medium | ada-visual.service.ts | COLOR
18 | Phase 3 - Visual & Design QA | Overlapping element detection | Bounding-box collision and clipping detection. Flag controls that overlap or become unclickable at any viewport. | Backend eng | 6 | 4 | 2026-11-30 | 2026-12-03 |  | Low | ada-visual.service.ts | OVERLAP
19 | Phase 3 - Visual & Design QA | UI alignment analysis | Detect misaligned elements, uneven spacing and broken grid layouts across breakpoints. Highest false-positive risk. | Backend eng | 7 | 5 | 2026-12-04 | 2026-12-10 |  | Low | ada-visual.service.ts | ALIGN
20 | Phase 3 - Visual & Design QA | Design-standard ingestion | Let a tenant upload a style guide / design-token file. Parse into a comparable rule set. Kiro-style project standards. | Backend eng | 5 | 4 | 2026-12-11 | 2026-12-16 |  | Medium | new: backend/src/services/ada-standards.service.ts | STYLEGUIDE
21 | Phase 3 - Visual & Design QA | Style-guide adherence check | Compare the live UI against the ingested standards and component rules. Report deviations per page. | Backend eng | 6 | 4 | 2026-12-17 | 2026-12-22 |  | Low | ada-standards.service.ts | STYLEGUIDE
22 | Phase 3 - Visual & Design QA | Visual-check tuning | False-positive reduction against two or three real client sites. Threshold calibration. Expect iteration here. | Backend eng + QA | 6 | 4 | 2026-12-23 | 2026-12-28 | M4 - Visual & design QA complete | Low | ada-visual.service.ts | ALIGN
23 | Phase 4 - Scoring & Reporting | Scoring model | Per-category scores and weighting into one overall health score. Documented and tenant-overridable. | Backend eng | 4 | 3 | 2026-12-29 | 2026-12-31 |  | Medium | new: backend/src/services/ada-score.service.ts | REPORT
24 | Phase 4 - Scoring & Reporting | Website health report | Scored audit: findings by page and severity, with evidence (screenshot + selector) attached to each. | Backend eng | 6 | 4 | 2027-01-01 | 2027-01-06 |  | Medium | backend/src/services/artifact-report.service.ts | REPORT
25 | Phase 4 - Scoring & Reporting | Trend across runs | Compare a scan to its predecessors. Surface regressions and improvements per category. | Backend eng | 4 | 3 | 2027-01-07 | 2027-01-11 |  | Medium | backend/src/services/report-archive.service.ts | REPORT
26 | Phase 4 - Scoring & Reporting | Export & notification | PDF/Excel export of the health report and email delivery on scan completion. | Backend eng | 4 | 3 | 2027-01-12 | 2027-01-14 | M5 - Health report GA-ready | High | backend/src/services/email.service.ts | REPORT
27 | Phase 5 - Frontend & UX | Replace the placeholder flow | Swap the ada-preview screen for the real wizard: app/URL picker, viewport and depth config, scan trigger. | Frontend eng | 5 | 4 | 2027-01-15 | 2027-01-20 |  | High | frontend/src/pages/ChatPage.tsx (ADA_SUITES, ada-preview) | UI
28 | Phase 5 - Frontend & UX | Live scan progress | Per-page progress in the chat panel and the pipeline sidebar, driven by SSE. | Frontend eng | 4 | 3 | 2027-01-21 | 2027-01-25 |  | High | frontend/src/pages/ChatPage.tsx | UI
29 | Phase 5 - Frontend & UX | Findings explorer | Browse and filter findings by severity, category and page. Evidence viewer with the offending element highlighted. | Frontend eng | 7 | 5 | 2027-01-26 | 2027-02-01 |  | Medium | new: frontend/src/pages/AdaFindingsPage.tsx | UI
30 | Phase 5 - Frontend & UX | Report page & Reports integration | Health report view, plus ADA runs listed alongside existing runs on the Reports page. | Frontend eng | 5 | 4 | 2027-02-02 | 2027-02-05 |  | High | frontend/src/pages/ReportsPage.tsx | UI
31 | Phase 5 - Frontend & UX | Bug Tracker integration | Raise a ticket straight from a finding, reusing the existing bug registration path. | Frontend eng | 3 | 2 | 2027-02-08 | 2027-02-09 |  | High | frontend/src/pages/BugTrackerPage.tsx, routes/bugs.routes.ts | UI
32 | Phase 5 - Frontend & UX | Feature toggle & role gating | Gate the suite behind a toggle and the existing role model so it can ship dark and enable per tenant. | Frontend eng | 2 | 2 | 2027-02-10 | 2027-02-11 | M6 - Feature complete (internal) | High | frontend/src/pages/FeatureTogglesPage.tsx, components/FeatureGate.tsx | UI
33 | Phase 6 - Hardening & Release | Multi-tenancy audit | Verify tenant_id filtering on every new query and route. Non-negotiable before any tenant sees it. | Tech lead | 2 | 2 | 2027-02-12 | 2027-02-15 |  | High | backend/src/routes/ada.routes.ts, db.ts | HARDEN
34 | Phase 6 - Hardening & Release | Budget & performance guards | Page caps, timeouts, cost ceilings and convergence guards so a large site cannot run away with the worker or the API spend. | Backend eng | 4 | 3 | 2027-02-16 | 2027-02-18 |  | Medium | backend/config/pipeline-definition.json | HARDEN
35 | Phase 6 - Hardening & Release | Security review | Credential handling for authenticated scans, encrypted at rest via the existing crypto util. Scan-target allowlisting. | Tech lead | 3 | 2 | 2027-02-19 | 2027-02-22 |  | High | backend/src/utils/crypto.ts | HARDEN
36 | Phase 6 - Hardening & Release | Test coverage | Unit tests per check plus an integration test that scans a fixture site with known defects. | QA + eng | 5 | 4 | 2027-02-23 | 2027-02-26 |  | Medium | backend/tests/ | HARDEN
37 | Phase 6 - Hardening & Release | Documentation | User guide, CLAUDE.md architecture update, operational runbook for failed scans. | Tech lead | 3 | 2 | 2027-03-01 | 2027-03-02 |  | High | CLAUDE.md | HARDEN
38 | Phase 6 - Hardening & Release | Client pilot & fix pass | Run against one real client site end to end. Triage findings with the client and fix what the pilot exposes. | Whole team | 5 | 4 | 2027-03-03 | 2027-03-08 |  | Medium | - | HARDEN
39 | Phase 6 - Hardening & Release | Release & rollout | Enable the toggle per tenant, monitor first production scans, close out. | Tech lead | 2 | 2 | 2027-03-09 | 2027-03-10 | M7 - GA release | High | - | HARDEN
|  |  |  | TOTAL | 171 | 128 |  | 2027-03-10
Formulas:
Start = WORKDAY([End, row above],1)
End = WORKDAY([Start],[Duration (working days)]-1)
End = [End, row above]

## Milestones
Milestones
Dates pull from the Roadmap tab. Cumulative effort is every task up to and including the milestone.
Milestone | Phase | Definition of done | Date | Cumulative effort (person-days) | Confidence
M1 - Approach approved | Phase 0 - Discovery & Spike | Approach validated by spike, scope and acceptance criteria signed off, schema designed. | 2026-09-24 | 12 | High
M2 - Scan pipeline runs end-to-end | Phase 1 - Scan Infrastructure | A scan can be triggered, crawls the target, records pages and streams progress - no checks wired yet. | 2026-10-21 | 38 | High
M3 - MVP: a11y + links shippable | Phase 2 - Deterministic Checks | MVP: accessibility (WCAG 2.2 AA), broken links and best-practice checks produce real findings. Recommended first release. | 2026-11-11 | 58 | High
M4 - Visual & design QA complete | Phase 3 - Visual & Design QA | All four visual checks plus style-guide adherence running and tuned against real sites. | 2026-12-28 | 103 | Low
M5 - Health report GA-ready | Phase 4 - Scoring & Reporting | Scored website health report with evidence, trend comparison, export and email. | 2027-01-14 | 121 | Medium
M6 - Feature complete (internal) | Phase 5 - Frontend & UX | Full UI: scan wizard, live progress, findings explorer, report page, bug-tracker hand-off. Behind a toggle. | 2027-02-11 | 147 | Medium
M7 - GA release | Phase 6 - Hardening & Release | Multi-tenancy, security and performance signed off. Piloted with a client and enabled in production. | 2027-03-10 | 171 | Medium
M3 is the recommended first release: highest-confidence checks, real user value, and it lands well before the full suite.

## Scope
Scope - the nine checks
Mirrors ADA_SUITES in frontend/src/pages/ChatPage.tsx (line ~113), which is what the placeholder screen renders. Effort pulls from the Roadmap tab by scope tag.
Check (as shown in the UI) | Group on screen | Scope tag | Delivered in phase | What it does | Technical approach | Confidence | Effort (person-days)
Broken & dead links / 404s | Links & site health | LINKS | Phase 2 | Crawl every internal and outbound link; report 404s, redirect chains and unreachable targets. | Custom crawler on the existing Playwright/Chromium setup. Well-understood problem. | High | 5
ADA / accessibility compliance | Accessibility & compliance | A11Y | Phase 2 | WCAG 2.2 AA: alt text, ARIA roles, focus order, keyboard traps, contrast - each mapped to a success criterion. | axe-core via @axe-core/playwright. Mature, deterministic rule engine - the one check with an off-the-shelf answer. | High | 9
UI alignment issues | Visual & design QA | ALIGN | Phase 3 | Misaligned elements, uneven spacing, broken grid layouts across breakpoints. | Bounding-box geometry from the live DOM, or rendered-baseline diff. No standard engine; needs the Phase 0 spike. | Low | 22
Inconsistent fonts / font sizes | Visual & design QA | FONT | Phase 3 | Font family, weight and size drift compared page to page. | Computed-style harvest, then clustering against the dominant set or a declared type scale. | Medium | 5
Incorrect colours / hex codes | Visual & design QA | COLOR | Phase 3 | Rendered colours checked against the approved brand palette and design tokens. | Computed-style harvest, compared to an ingested token set. Needs the palette as input. | Medium | 5
Buttons or elements overlapping | Visual & design QA | OVERLAP | Phase 3 | Controls that collide, clip or become unclickable at any viewport. | Bounding-box collision detection plus hit-testing. Overlap is common and often intentional - tuning matters. | Low | 6
Style guide / design standards adherence | Visual & design QA | STYLEGUIDE | Phase 3 | The live UI compared against documented design standards and component rules. | Tenant uploads a style guide or token file; agent treats it as the source of truth (Kiro-style steering doc). | Low | 11
General web best practices | Accessibility & compliance | BESTPRACTICE | Phase 2 | Semantic HTML, page metadata, image sizing, console errors, mixed content. | Lighthouse-style rule set, implemented directly against the page. | Medium | 5
Website health / audit report | Output | REPORT | Phase 4 | One scored audit per run: score per category, findings ranked by severity with page and element, trend across runs. | Scoring model over normalised findings, rendered through the existing report/artifact services. | Medium | 22
[6 empty] | Checks total | 90
Note: the checks total (90) is less than the roadmap total (171) because scan infrastructure, frontend and hardening effort is not attributed to any single check. Shared visual tooling (the computed-style harvester, the Phase 0 spike and the tuning pass) is tagged to UI alignment, so that row reads high relative to the three visual checks that also depend on it.

## Risks
Risk register
Ordered by exposure. The top three all sit in Phase 3.
Risk | Likelihood | Impact | Why it matters | Mitigation | Owner
Visual checks produce too many false positives to be usable | High | High | Alignment and overlap have no standard rule engine. A check that cries wolf gets switched off and the phase is wasted. | Phase 0 spike before committing. Budget explicit tuning time (task 22). Ship visual checks behind a per-tenant toggle, warn-only at first. | Tech lead
Phase 3 effort grows beyond estimate | High | Medium | 45 of 171 person-days sit in the least-certain phase. A baseline-diff approach would cost materially more than geometry analysis. | Re-estimate Phase 3 at the M1 gate once the spike lands. Ship M3 first so a Phase 3 overrun does not block all user value. | Tech lead
Style-guide adherence has no input to check against | Medium | High | The check is meaningless unless the tenant actually has documented design standards in a parseable form. Many will not. | Confirm with the pilot client during Phase 0 that a usable style guide or token file exists. Otherwise defer this check. | Product
Scan cost and runtime on large sites | Medium | Medium | Every check runs per page. A large site multiplies browser time and, where the LLM is involved, API spend. | Hard page caps and timeouts from Phase 1 (existing budget-guard pattern). Cost ceiling per scan, surfaced before the run starts. | Backend eng
Authenticated scans need stored credentials | Medium | High | Scanning past a login means holding tenant credentials, which widens the security surface. | Reuse the existing encrypted credential store (backend/src/utils/crypto.ts). Security review is a gating task in Phase 6. | Tech lead
axe-core version drift vs WCAG updates | Low | Medium | Rule sets and success criteria change; findings could go stale or shift between releases. | Pin the axe-core version, record it on every scan, and treat upgrades as a deliberate change with a re-baseline. | Backend eng
Competing priorities pull engineers off the feature | Medium | High | The plan assumes 2 engineers at 80%. Real allocation on this codebase has historically been lumpier. | Track actual capacity against the Assumptions tab; recalculate dates monthly rather than defending the original date. | Delivery lead